## Gantt Chart
PBL Code | PBLMK232-54
PROJECT TITLE | Mini CNC Milling Using Integrated Servo Motor
No | Description Task |  | PIC | Status | Achievement in percentage | Team | Plan/Actual | February | March | [18 empty] | April | [6 empty] | May | [22 empty] | June | [19 empty] | Juli
[8 empty] | Date | Dates | [18 empty] | Dates | [6 empty] | Dates | [22 empty] | Dates | [19 empty] | Dates
[8 empty] | 29 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12
1. | Planning and Team Discussion |  | Budiman Zahri
| 1.1 | First discussion online with Project Manager |  | Done | 100% | All | PLAN | bar: Date 29
ACTUAL | bar: Date 29
| 1.2 | Member registration on PBL ready website |  | Done | 100% | All | PLAN | bar: Date 29
ACTUAL | bar: Date 29
| 1.3 | Create timeline |  | Done | 100% | Galuh | PLAN | bar: Dates 4
ACTUAL | bar: Dates 6
| 1.4 | Offline discussion with project manager |  | Done | 100% | All | PLAN | bar: Dates 1
ACTUAL | bar: Dates 1
| 1.5 | Identify team members and assign roles. |  | Done | 100% | Budi | PLAN | bar: Dates 4
ACTUAL | bar: Dates 6
| 1.6 | Discussion about the list of BHP that will be submitted |  | Done | 100% | All | PLAN | bar: Dates 6
ACTUAL | bar: Dates 29
| 1.7 | Ensure the targets that will result from this PBL |  | Done | 100% | Budi | PLAN | bar: Dates 22
ACTUAL | bar: Dates 24
| 1.8 | Search information about CNC Milling that is worked on in the project. |  | Done | 100% | Galuh | PLAN | bar: Dates 6
ACTUAL | bar: Dates 22
2. | Planner and HR |  | Galuh Candra Kirana
| 2.1 | Create the RPP (Rencana Pelaksanaan Proyek) |  | Done | 100% | Galuh | PLAN | bar: Dates 4
ACTUAL | bar: Dates 6
| 2.2 | Create a BHP list |  | Done | 100% | Galuh | PLAN | bar: Dates 6
ACTUAL | bar: Dates 29
| 2.3 | Ensure smooth submission of BHP from ordering until the goods are ready for use |  | Done | 100% | Galuh | PLAN | bar: Dates 3
ACTUAL | bar: Dates 21
| 2.4 | Create attendance to ensure team members are working according to their tasks. |  | Done | 100% | Galuh | PLAN | bar: Dates 6
ACTUAL | bar: Dates 28
3. | Mechanical Design |  | Eldio Utama
| 3.1 | Download software Soliwork |  | Done | 100 | Eldio | PLAN | bar: Dates 1 to Dates 4
ACTUAL | bar: Dates 1 to Dates 4
| 3.2 | Measuring the parts of the tool to be designed |  | Done | 100 | Eldio | PLAN | bar: Dates 23 to Dates 3
ACTUAL | bar: Dates 23 to Dates 3
| 3.3 | Create a design |  | Done | 100 | Eldio | PLAN | bar: Dates 9 to Dates 21
ACTUAL | bar: Dates 9 to Dates 21
4. | Machanical |  | Mohammad Ihsan
| 4.1 | Checking Raw Material and Request Material Approval |  | Done | 100% | Ihsan | PLAN | bar: Dates 1 to Dates 4; Dates 6; Dates 22 to Dates 2
ACTUAL | bar: Dates 6; Dates 22 to Dates 2
| 4.2 | Assembly Z Axis |  | Done | 100% | Ihsan | PLAN | bar: Dates 29 to Dates 9
ACTUAL | bar: Dates 8 to Dates 27
| 4.3 | Assembly Spindell |  | Done | 100% | Ihsan | PLAN | bar: Dates 21 to Dates 29
ACTUAL | bar: Dates 24 to Dates 30
| 4.4 | Assembly Servo Motor |  | Done | 100% | Ihsan | PLAN | bar: Dates 7 to Dates 11
ACTUAL | bar: Dates 11 to Dates 13
| 4.5 | Assembly of other supporting materials |  | Done | 100% | Ihsan | PLAN | bar: Dates 19 to Dates 20
ACTUAL | bar: Dates 20 to Dates 21; Dates 27 to Dates 28
5. | Electrical Diagram |  | Ilham Zulfadillah
| 5.1 | Make electrical diagrams in accordance with electrical wiring |  | Done | 100 | Ilham | PLAN | bar: Dates 16 to Dates 20
ACTUAL | bar: Dates 20 to Dates 28
| 5.2 | Perform wiring check |  | Done | 100 | Ilham | PLAN | bar: Dates 3 to Dates 28
ACTUAL | bar: Dates 7 to Dates 28
6. | Electrical Wiring |  | Muhammad Fatzri Sabila
| 6.1 | Checking Raw Material and Request Material Approval |  | Done | 100% | Fatzri | PLAN | bar: Date 29 to Dates 4; Dates 6; Dates 22 to Dates 23
ACTUAL | bar: Dates 1 to Dates 4; Dates 6; Dates 22 to Dates 23
| 6.2 | Install power supply |  | Done | 100% | Fatzri | PLAN | bar: Dates 24 to Dates 30
ACTUAL | bar: Dates 21
| 6.3 | Install electrical for X, Y, and Z axis |  | Done | 100% | Fatzri | PLAN | bar: Dates 1 to Dates 8
ACTUAL | bar: Dates 24 to Dates 25
| 6.4 | Adjust part for moving X, Y, and Z axis |  | Done | 100% | Fatzri | PLAN | bar: Dates 9 to Dates 16
ACTUAL | bar: Dates 25 to Dates 26
| 6.5 | Trubleshooting electrical |  | Done | 100% | Fatzri | PLAN | bar: Dates 17 to Dates 6
ACTUAL | bar: Dates 25 to Dates 28
| 6.6 | Testing |  | Done | 100% | Fatzri | PLAN | bar: Dates 7 to Dates 28
ACTUAL | bar: Dates 26 to Dates 28
7. | Program Interface |  | Budiman Zahri
| 7.1 | study documentation of Servo motor, C#, C++, Accelstepper |  | Done | 100 | Budi | PLAN | bar: Date 29 to Dates 4; Dates 6; Dates 22 to Dates 25
ACTUAL | bar: Dates 22 to Dates 2
| 7.2 | Create the program interfaces CNC Milling |  | Done | 100 | Budi | PLAN | bar: Dates 3 to Dates 28
ACTUAL | bar: Dates 21 to Dates 28
| 7.3 | Testing |  | Done | 100 | Budi | PLAN | bar: Dates 20 to Dates 28
ACTUAL | bar: Dates 20 to Dates 28
8. | QA/QC |  | Rocky S
| 8.1 | Verifying product conformance to specifications |  | Done | 100 | Rocky | PLAN | bar: Dates 1 to Dates 4
ACTUAL | bar: Dates 6; Dates 22 to Dates 23
| 8.2 | Identify and report quality issues |  | Done | 100 | Rocky | PLAN | bar: Dates 1 to Dates 2
ACTUAL | bar: Dates 7 to Dates 8; Dates 17 to Dates 20
| 8.3 | Provide recommendations for process improvement |  | Done | 100 | Rocky | PLAN | bar: Dates 25 to Dates 26
ACTUAL | bar: Dates 24 to Dates 28; Dates 12 to Dates 13
9 | Report PBL |  | Galuh Candra Kirana
| 9.1 | Create a PBL report |  | Done | 100% | Galuh | PLAN | bar: Dates 2 to Dates 3
ACTUAL | bar: Dates 4 to Dates 12

## Konfigurasi
STATUS | Information | Nama PIC | Information
To Do |  | Galuh
In Progress |  | Ikhsan
Waiting Approval |  | Budi
Done |  | Rocky
Cancelled |  | Ilham
Fatzri
Eldio
All